## Test Dev FMEA
Failure Mode and Effects Analysis (Quality Risks Analysis) Form
System Name: |  | Leave blank | Model/Product: |  |  |  | 25422229
Product Manager: |  | Leave blank | Target Release Date: |  |  |  | 8 September 2024
Project Manager: |  | Leave blank | Prepared By: |  |  |  | Thu Thuy NGUYEN
Other Stakeholders: |  | Leave blank | FMEA Date: |  |  |  | Leave blank
Test Manager: |  | Leave blank | FMEA Revision date: |  |  |  | Leave blank
Risk ID Number | Quality Risk Category | Failure Mode/Quality Risk/Effect | Severity | Priority | Risk Priorty Number | Recommended Action | Requirement Tracing
R001 | System functionality | Users have to register/ log on before booking, which might create unnecessary complications for the system and can make customers feel complex and tangled. In other cases, customers may be unable to log in, so they cannot make a booking. | 3 | 2 | 6 | Create a guest role so customers can book a table as a guest without registering/ logging in. | 1.5 Assumptions 2.2.1 in 2.2 Make a reservation
R002 | System functionality | The system might fail to detect and handle duplicate patron registrations, cluttering the database with redundant entries. | 2 | 2 | 4 | Implement duplicate checking algorithms that compare key fields (e.g., email, phone number) to detect and prevent multiple registrations for the same user. | 1.5 Assumptions
R003 | System functionality | Although the first phase doesn’t include payment, the framework must be set up. Inadequate preparation for future payment features could require significant redesign. | 2 | 5 | 10 | Design the system allowing future integration of payment gateways. Ensure the system architecture can accommodate payment features without major redesigns. | 1.5 Assumptions
R004 | System functionality | If the system fails to lock tables properly when a reservation is being made, multiple users might reserve the same table, leading to conflicts. | 1 | 1 | 1 | Implement automated update whenever user access to the system. | 2.2.10 in 2.2 Make a reservation
R005 | System functionality | Customers can modify/ cancel reservations at the last minute, so the staff might miss the notification, leading to overbooking or cancelled tables still being set up. | 4 | 5 | 20 | Put a time limit for modifying/ cancelling reservations. For example, bookings cannot be modified/ cancelled before 2 hours. | 2.5.1 in 2.5 Modify/ Cancel Reservation
R006 | System operations | Managers have to review and confirm bookings before confirmation, which can create unnecessary complications for the system. Moreover, it might take a long time for customers to wait. | 5 | 4 | 20 | Having an automatic confirmation function. | 1.5 Assumptions
R007 | System operations | Only sending the notification as a message in the system can make users miss it easily. | 3 | 4 | 12 | The system should send email and SMS via phone number as well. | 2.2.11 in 2.2 Make a reservation 2.5.6 & 2.5.11 in 2.5 Modify/ Cancel Reservation
R008 | System operations | Weekly maintenance might disrupt service availability if not managed carefully, potentially alienating customers. | 5 | 5 | 25 | Communicate downtime to users in advance. Consider implementing rolling updates. | 4.7 System maintainance
R009 | System opeartions | The system must achieve 99.9% availability, which leaves little room for error. Any operational missteps could lead to exceeding allowable downtime. | 2 | 2 | 4 | Implement automatic failover processes and conduct regular disaster recovery drills to ensure the system can meet its 99.9% availability target. | 4.6.1 in 4.6 Reliability
R010 | Data quality | The database must manage reservations, table avalable status, and user data efficiently. Poor schema design could lead to slow queries and data inconsistency. | 4 | 4 | 16 | Use normalized database schemas and index critical fields for performance. Regularly review and optimize database queries and structures as the system scales. | 2.6 View database
R011 | Data quality | If the database isn't designed to scale, it may cause performance bottlenecks as the customer base grows. | 3 | 4 | 12 | Design the database with scalability in mind, using techniques such as sharding, indexing, and database replication. Consider using cloud-based database services that can scale automatically. | 2.6 View database
R012 | Capacity & Volume | The system support at least 100 users concurrently. Failure to scale appropriately might cause system crashes during peak times. | 4 | 3 | 12 | Increase the maximum capacity. | 4.4.2 in 4.4 Perfomance
R013 | Security | Without strong anti-phishing measures, users might fall victim to fake login pages or phishing emails, compromising their accounts. | 5 | 5 | 25 | Implement email validation measures and use secure communication channels. Educate users on recognizing phishing attempts. | 1.5 Assumptions 2.2.1 in 2.2 Make a reservation
R014 | Security | Lack of security methods for user authentication, especially for admin roles, could allow unauthorized access to sensitive functions. | 3 | 3 | 9 | Implement multi-factor authentication for admin users. Regularly audit access logs for any suspicious activity. | 4.3 Sercurity
R015 | Security | The requirement that patron information must be secure and encrypted might not be adequately implemented, leading to potential data breaches. | 3 | 3 | 9 | Implement strong encryption protocols for data at rest and in transit. Regularly update and patch all security systems. | 1.6 Constraints 4.3.3 in 4.3 Security
R016 | Security | Backups that are not encrypted might expose sensitive customer data in case of breaches. | 3 | 3 | 9 | Ensure that all backup data is encrypted both at rest and in transit. Use strong encryption algorithms for all backups | 4.5 Backup and Recovery
R017 | User interface | Some people don't understand the 24-hour clock time format. | 5 | 5 | 25 | The system should have options for people to adjust the time format. | 3.3 in 3. Data requirements
R018 | User interface | A complex navigation structure could confuse users and reduce usability, resulting in frustration and abandonment. | 5 | 4 | 20 | Simplify the navigation by grouping related functions logically. | 2.1.2 in 2.1 General 2.3.4 in 2.3 Browse Menu
R019 | User interface | Creating a responsive, dynamic website that displays correctly across all devices and browsers could be difficult, leading to a poor user experience. | 5 | 4 | 20 | Test the display on various screen sizes and browsers to ensure consistency | 4.1 Compatibility
R020 | User interface | The requirement doesnot mention another language, so user cannot change their language. If the restaurant expands or attracts non-English-speaking users, not designing the system for easy translation could limit market reach. | 5 | 5 | 25 | Making sure the design supports easy translation. | 5. Interface Requirements
R021 | Training | Inadequate training staff could lead to operational inefficiencies and customer dissatisfaction. | 4 | 5 | 20 | Offer ongoing training sessions, especially after major updates or new feature releases. | 1.3 Stakeholders and users
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on A4: The person responsible for the product from inception to end-of-life.
Note on A5: The person responsible for managing the development effort up to the release point.
Note on A6: Other key quality and testing stakeholders affected by the quality of the system and/or the testing process.
Note on A7: The test manager responsible for assessing quality per this risk analysis and implementing Integration and System Test mitigation measures.
Note on A9: An identifier for the risk category and for the specific failure modes. This ID can be used to trace quality risk coverage by test cases.
Note on B9: The category or type of quality risk that is identified. This is used to group similar types of risk together in the spreadsheet. By grouping the risks it is easier to identify duplicates and prepare individual tests that will test multiple risks. For example - 'Security' could be a category addressing issues around passwords, user registration etc. A list of suggested categories is in a separate tab of this spreadsheet.
Note on C9: The specific problem or kind of failure that is being checked. These can be worded in a affirmative or negative - so long as the failure risk is clear.
Note on D9: Severity: is the impact of the defect on the application; 1. Blocker: system crash, corruption of data, critical functionality missing. 2. Critical: failure to save data; important functions missing, security issues. 3. Major: website hangs; script error, functions don’t work correctly 4. Important: UI issue; small function issue. 5. Minor: cosmetic problem.
Note on E9: Priority: reflects the impact of the defect on the business and consequently how quickly developers need to find and fix it. 1. Urgent: to be fixed immediately. 2. High: to be resolved in the next release. 3. Medium: defects the must be fixed before shipment 4. Important: defects that can be fixed after shipment 5. Low: defects are not as strong as desirable, can be deferred to next release.
Note on F9: This is the risk priority number, which is the severity (how bad) times the priority (expected customer impact) times the likelihood (will it get to the customers). Since we use 1-5 for all three parameters, this ranges from 1 (most dangerous quality risk) to 125 (least dangerous quality risk).
Note on G9: Assuming the problem happens - determine who and how the problems should be addressed.
Note on H9: A clear reference to the requirement that is being tested. State the document name, page number, paragraph and sentence.

## Severity Priority
Severity: is the impact of the defect on the application;
1. Blocker: system crash, corruption of data, critical functionality missing.
2. Critical: failure to save data; important functions missing, security issue.
3. Major: website hangs; script error, functions don’t work correctly
4. Important: UI issue; small function issue.
5. Minor: cosmetic problem.
Priority: reflects the impact of the defect on the business and consequently how quickly developers need to find and fix it.
1. Urgent: to be fixed immediately.
2. High: to be resolved in the next release.
3. Medium: defects the must be fixed before shipment
4. Important: defects that can be fixed after shipment
5. Low: defects are not as strong as desirable, can be deferred to next release.

## Quality Risk Categories
Suggested quality risk categories
System functionality
User Interface
Transaction processing
Data Quality
System operations
Installation & upgrades
Capacity & Volume
Reliability, availability and stability
Stress test (break test)
Performance testing
Date & time handing
Localisation
Documentation
Training
Networks
Business Processes
Configuration
Response time
Compliance (standards & legal)
Security
Environment
Power & Heat
Business continuity
Infrastructure
…and if you don't think the risk fits one of these create a new one (just a few key words)